## Example
Gantt Chart Template for Yukon COVID-19 Recovery Research Program
Note: This Template File contains two worksheets - This worksheet, with an example of Gantt Chart for illustration purposes, another with a blank Gantt Chart template, for your project steps and timeline. Additional guidance is found in the Call for Proposals and Instructions for Applicants
Project Title:
Project Lead:
Planned Period of Work for Identified Task
Sample Project Task List | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01
Securing permissions and licenses | bar: 2022-04-01
Literature review | bar: 2022-04-01
Methods development | bar: 2022-05-01 to 2022-07-01
Engaging with partners and contributors on methods | bar: 2022-05-01 to 2022-06-01
Developing collection tools and materials | bar: 2022-06-01 to 2022-07-01
Training | bar: 2022-06-01 to 2022-07-01
Recruiting participants | bar: 2022-07-01 to 2022-08-01
Conducting interviews | bar: 2022-08-01 to 2022-09-01
Analyzing responses | bar: 2022-09-01 to 2022-10-01
Summarizing and reporting | bar: 2022-11-01 to 2022-12-01
Knowledge mobilization / sharing | bar: 2022-12-01 to 2023-03-01
Engaging with partners and contributors on knowledge mobilization activities | bar: 2022-12-01 to 2023-01-01
Conducting outreach at end-user organizations (webinars) | bar: 2023-01-01 to 2023-02-01
Public communication of results (news release, website) | bar: 2023-03-01
Publishing results on YG Open Data portal | bar: 2023-03-01

## Blank Template
Gantt Chart Template for Yukon COVID-19 Recovery Research Program
Please carefully review and follow guidelines and requirements in the Call for Proposals and Instructions for Applicants.
Project Title:
Project Lead:
Planned Period of Work for Identified Task (Highlight Cells as needed to reflect planned timing for your task list)
Task List (Edit labels and add rows as needed to reflect your project activities) | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01
Task 1
Task 2
Task 3
Task 4
Task 5
Task 6
Task 7
Task 8
Task 9
Task 10
Task 11
Task 12
Task 13
Task 14
Task 15